## Sheet1
0 |  |  | Employee Booking System
Daily Time Sheet for :Kashyap Gundepudi |  |  | 158142-EBS | [27 empty] | Month : |  |  | 2018-10-01
Task Desc |  | Task Category | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | Total
| Phase |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Available Hrs |  |  | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 27
Over Time |  |  | 2.5 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
Total Hrs. |  |  | 10.5 | 0 | 9.5 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 31
0
Understanding Case study | Requirements | Main Task(Prep.) | [31 empty] | 1 | bar: 158142-EBS M 1
Understanding the URS and prepare reverse presentation | Requirements | Main Task(Prep.) | 158142-EBS M 1: 0.5 | 0.5
Understanding the Prototype and class diagram | Requirements | Main Task(Prep.) | [31 empty] | 1 | bar: 158142-EBS M 1
Unit Test Plan for AddEmployee Module | Unit Test Planning | Main Task(Prep.) | [31 empty] | 1 | bar: 158142-EBS M 1
LLD | Training | Main Task(Prep.) | [31 empty] | 0
LLD preparation for Add Employee | Low Level Design | Main Task(Prep.) | [31 empty] | 1 | bar: 158142-EBS M 1
UTP Review and Tracebility | Training | Main Task(Prep.) | [31 empty] | 2
UTP Review for AddEmployee Module | Unit Testing | Review | [31 empty] | 0
Tracebility | Low Level Design | Main Task(Prep.) | [31 empty] | 0
Tracebility | Low Level Design | Main Task(Prep.) | [31 empty] | 0
UTP Rework for Add Employee Module | Unit Test Planning | Rework | [31 empty] | 1 | bar: Month : M 29
LLD Review for Add Employee Module | Unit Testing | Review | [31 empty] | 0
LLD Rework for UploadEmployee Module | Low Level Design | Rework | [31 empty] | 0
Coding | Training | Main Task(Prep.) | [31 empty] | 1 | bar: 158142-EBS W 3
UTP Second Review for AddEmployee Module | Unit Testing | Review | [31 empty] | 0
UTP Second Rework for ViewEmployee Module | Unit Test Planning | Rework | [31 empty] | 0
Tracebility | Low Level Design | Main Task(Prep.) | [31 empty] | 0
DB Design | Coding | Main Task(Prep.) | 158142-EBS M 1: 2 | 2
Understanding the LLD for Search Employee | Coding | Main Task(Prep.) | [31 empty] | 1 | bar: 158142-EBS M 1
Coding for Travel plan | Coding | Main Task(Prep.) | [31 empty] | 0
Coding for Login | Coding | Main Task(Prep.) | [31 empty] | 1 | bar: 158142-EBS W 3
Coding for Search | Coding | Main Task(Prep.) | [31 empty] | 1 | bar: 158142-EBS W 3
Coding for Travel plan | Coding | Main Task(Prep.) | bar: 158142-EBS W 3
Discussion with mentor | Training | Meeting | [31 empty] | 0
Consolidating LLD | Low Level Design | Rework | 158142-EBS T 4: 2 | 2
Coding for Travel plan | Coding | Main Task(Prep.) | [31 empty] | 0
Meeting with mentor | Training | Meeting | [31 empty] | 0
Coding for Delete plan | Coding | Main Task(Prep.) | [31 empty] | 0
Coding for Delete plan | Coding | Main Task(Prep.) | [31 empty] | 0
Self Review for Travel plan | Coding | Review | [31 empty] | 1 | bar: 158142-EBS W 3
Self Review for Travel plan | Coding | Review | [31 empty] | 0
Rework for SearchPlan | Coding | Rework | [31 empty] | 1 | bar: 158142-EBS W 3
Rework for Search employee | Coding | Rework | [31 empty] | 1 | bar: 158142-EBS T 4
Peer Review For Add Employee | Coding | Review | 158142-EBS W 3: 0.5; 158142-EBS T 4: 1 | 1.5
Peer Testing for Search | Unit Testing | Review | [31 empty] | 0
Test Result Review | Coding | Review | bar: Month : M 29
Search Employee rework after peer review | Coding | Rework | [31 empty] | 1 | bar: 158142-EBS T 4
Code Integration | Integration Test Planning | Main Task(Prep.) | 158142-EBS W 3: 2 | 2
Integration Testing | Integration Testing | Main Task(Prep.) | 158142-EBS M 1: 2; 158142-EBS W 3: 1; Month : M 29: 1 | 4
Rework | Coding | Rework | [31 empty] | 1 | bar: 158142-EBS T 4
Test Result Review | Coding | Review | [31 empty] | 0
Presentation preparation | Miscellaneous | Main Task(Prep.) | [31 empty] | 1 | bar: 158142-EBS M 1
Deployment | Release | Main Task(Prep.) | [31 empty] | 1 | bar: 158142-EBS T 4
1 | bar: 158142-EBS T 4
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Note on AI2: Month Start Date. Please enter Month start date. (e.g. 01 Aug 02)
Note on AI7: Total Effort for the Month
Note on A8: 500155: Enter Description of the task For Ex MRID, PP Preparation, Metrics Preparation etc...
Note on C8: Leave will not be accounted in the Totals.
Company Internal