## Sheet1
0 |  |  | Employee Booking System
Daily Time Sheet for :Vikram Karnati |  | Main Task(Prep.) | 158163-EBS | [27 empty] | Month : |  |  | 2018-10-01
Task Desc |  | Task Category | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | Total
| Phase |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Available Hrs |  |  | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 27
Over Time |  |  | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
Total Hrs. |  |  | 10 | 0 | 10 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 31
0
0 | Requirements | Main Task(Prep.) | [31 empty] | 1 | bar: 158163-EBS M 1
Understanding Case study | Requirements | Main Task(Prep.) | 158163-EBS M 1: 0.5 | 0.5
Understanding the URS and prepare reverse presentation | Requirements | Main Task(Prep.) | [31 empty] | 1 | bar: 158163-EBS M 1
Understanding the Prototype and class diagram | Unit Test Planning | Main Task(Prep.) | [31 empty] | 1 | bar: 158163-EBS M 1
Unit Test Plan for AddEmployee Module | Training | Main Task(Prep.) | [31 empty] | 0
LLD | Low Level Design | Main Task(Prep.) | [31 empty] | 1 | bar: 158163-EBS M 1
LLD preparation for Add Employee | Low Level Design | Main Task(Prep.) | [31 empty] | 2 | bar: 158163-EBS M 1
UTP Review and Tracebility | Training | Review | 158163-EBS M 1: 0.5; 158163-EBS W 3: 0.5 | 1
UTP Review for AddEmployee Module | Unit Testing | Review | [31 empty] | 1 | bar: 158163-EBS T 4
Tracebility | Low Level Design | Main Task(Prep.) | [31 empty] | 0
Tracebility | Unit Testing | Review | [31 empty] | 1 | bar: Month : M 29
UTP Rework for Add Employee Module | Unit Testing | Rework | [31 empty] | 0
LLD Review for Add Employee Module | Low Level Design | Review | [31 empty] | 0
LLD Rework for UploadEmployee Module | Low Level Design | Rework | [31 empty] | 1 | bar: 158163-EBS W 3
Coding | Training | Main Task(Prep.) | [31 empty] | 0
UTP Second Review for AddEmployee Module | Low Level Design | Rework | [31 empty] | 1 | bar: 158163-EBS M 1
UTP Second Rework for ViewEmployee Module | Unit Testing | Review | [31 empty] | 0
Tracebility | Unit Testing | Rework | [31 empty] | 0
DB Design | Coding | Main Task(Prep.) | [31 empty] | 1 | bar: 158163-EBS W 3
Understanding the LLD for Search Employee | Coding | Main Task(Prep.) | 158163-EBS W 3: 2 | 2
Coding for Travel plan | Coding | Main Task(Prep.) | [31 empty] | 0
Coding for Login | Coding | Main Task(Prep.) | [31 empty] | 0
Coding for Search | Coding | Main Task(Prep.) | bar: 158163-EBS W 3
Coding for Travel plan | Training | Meeting | [31 empty] | 0
Discussion with mentor | Low Level Design | Rework | [31 empty] | 1 | bar: 158163-EBS T 4
Consolidating LLD | Coding | Main Task(Prep.) | [31 empty] | 0
Coding for Travel plan | Training | Meeting | [31 empty] | 0
Meeting with mentor | Coding | Main Task(Prep.) | [31 empty] | 0
Coding for Delete plan | Coding | Main Task(Prep.) | [31 empty] | 0
Coding for Delete plan | Coding | Review | [31 empty] | 1 | bar: 158163-EBS W 3
Self Review for Travel plan | Coding | Main Task(Prep.) | [31 empty] | 0
Self Review for Travel plan | Coding | Rework | [31 empty] | 0
Rework for SearchPlan | Coding | Rework | [31 empty] | 0
Rework for Search employee | Coding | Review | 158163-EBS W 3: 0.5 | 0.5
Peer Review For Add Employee | Coding | Review | [31 empty] | 1 | bar: 158163-EBS T 4
Peer Testing for Search | Unit Testing | Review | bar: 158163-EBS T 4; Month : M 29
Test Result Review | Unit Testing | Review | [31 empty] | 1 | bar: 158163-EBS T 4
Search Employee rework after peer review | Coding | Review | [31 empty] | 1 | bar: 158163-EBS W 3
Code Integration | Coding | Rework | 158163-EBS M 1: 1; 158163-EBS W 3: 2; Month : M 29: 1 | 4
Integration Testing | Integration Test Planning | Main Task(Prep.) | [31 empty] | 1 | bar: 158163-EBS T 4
Rework | Integration Testing | Main Task(Prep.) | [31 empty] | 1 | bar: 158163-EBS T 4
Test Result Review | Coding | Rework | 158163-EBS M 1: 2 | 2
Presentation preparation | Coding | Review | [31 empty] | 1 | bar: 158163-EBS T 4
Deployment | Miscellaneous | Main Task(Prep.) | [31 empty] | 0
| Release | Main Task(Prep.) | [31 empty] | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Note on AI2: Month Start Date. Please enter Month start date. (e.g. 01 Aug 02)
Note on AI7: Total Effort for the Month
Note on A8: 500155: Enter Description of the task For Ex MRID, PP Preparation, Metrics Preparation etc...
Note on C8: Leave will not be accounted in the Totals.
Note on A9: 500155: Enter Description of the task For Ex MRID, PP Preparation, Metrics Preparation etc...
Company Internal
Company Internal